## Procurement timetable
[14 empty] | Updated |  | 2020-10-30
2018-07-04
Procurement timetable
FUT procurement identification number (FUT id nr) | Object designation / assignment (name of the procurement) | Description/ scope | Type | Project (Extension part) | For participation in procurement registration is required with consulting brokers or qualification system | Only prequalified suppliers in TransQ can participate Trans Q code | Contract type | Scheduled time for qualification of suppliers | Scheduled time for invitation to tender | Scheduled time for submission of tenders | Planned assignment start | Estimated cost SEK million | Link to further information | Procurement certainty | Procurement certainty | Comment
2651 | Building and installation works 7 Stations (Sofia, Hammarby kanal, Gullmarsplan, Slakthuset, Sickla, Järla and Nacka C) | The contract comprises framework completions and installations for entrances, ticket halls, mezzanines, platforms, technical plan, service tunnel, ventilation shaft, fire shaft, etc. | Building and installation works | Nacka-southern suburbs | Precualification in TransQ is required | Yes 9.4.1 – 9.4.9 or 9.4.99 | Design & Build Contract | 2021-01-20 | 2021-06-15 | 2022-03-01 | 2022-06-01 | 600-700 |  | Red - information uncertain |  | This contract replaces former construction contracts regarding: - Sofia & Hammarby kanal - Gullmarsplan & Slakthuset - Sickla, Nacka och Järla
3711 | Rock excavation and civil works Hagastaden, including building and installation | The contracts comprise rock shafts for tunnels, platform rooms, vertical shafts. Works with heavy steel and concrete framework for Hagastaden station and connecting tunnels to Odenplan and Hagalund. Earth and foundation works for ticket halls. The contracts comprise, among other things, framework completions with light walls, wall panels, forging, glass partitions, false ceiling, floor and other surface layers. Installations for heating, water, sewage, sprinklers, ventilation, lighting, electricity/telecom, lifts, escalators for complete station. | Rock excavation and civil works | Arenastaden | Precualification in TransQ is required | Yes 9.4.1 – 9.4.9 or 9.4.99 | Build only contract | ongoing | Ongoing procurement | 2020-11-20 | 2021 Q1 | >1000 |  | Green - information certain (within 3 months) | Red - information uncertain | Railwayplan - estimated July 2020
3717 | Rock excavation and civil works Arenastaden and Södra Hagalund | The assignment includes construction of a Access tunnel and preparation of an establishment area, rock shafts for tunnels, platform rooms, vertical shafts. Works with heavy steel and concrete framework for Arenastaden oand Södra Hagalund station and connecting tunnels to Hagastaden. Earth and foundation works for ticket halls. | Rock excavation and civil works | Arenastaden | Precualification in TransQ is required | Yes 9.4.1 – 9.4.9 or 9.4.99 | Build only contract | ongoing | Ongoing procurement | 2021-01-28 | 2021 Q2 | > 1 000 |  | Green - information certain (within 3 months) | Red - information uncertain | Replaces 3716, 3712 and 3713. Railwayplan - estimated July 2020
3727 | Building and installation works Södra Hagalund and Arenastaden | The contracts comprise, among other things, framework completions with light walls, wall panels, forging, glass partitions, false ceiling, floor and other surface layers. Installations for heating, water, sewage, sprinklers, ventilation, lighting, electricity/telecom, lifts, escalators for complete station. | Building and installation works | Arenastaden | Precualification in TransQ is required | Yes 9.4.1 – 9.4.9 or 9.4.99 | Build only contract | 2023-Q2 | 2023-Q3 | 2024-Q2 | 2024-Q3 | >1000 |  | Red - information uncertain |  | Replaces 3722 och 3723. Railwayplan - estimated July 2020
3742 | BEST assembly (Track-, Electrical-, Signal- and Telecommunication works) | The contract comprises assembly works for new rail installation. Rail and switch assembly, third-rail installation, low-voltage installations in rail tunnels, signals, etc. | BEST (Track-, Electrical-, Signal- and Telecommunication works) | Arenastaden | Precualification in TransQ is required | Yes 9.1.1 | Build only contract | 2023-Q1 | 2023-Q1 | 2023-Q4 | 2024-Q1 | 200-400 |  | Red - information uncertain | Red - information uncertain
3745 | LS Hälsingehöjden | Rebuilding of existion rectifier substation in Hälsingehöjden | Building and installation works, electrical | Arenastaden |  |  |  |  | 2021-Q2 | 2021-Q3 | 2022-Q1 | <50 |  | Red - information uncertain |  | new
4715 | Concrete tunnel | Cocrete tunnel | Rock excavation and civil works | Barkarby | Precualification in TransQ is required |  | Design & Build Contract | 2023-01-01 | 2023-03-02 | 2023-10-31 | 2023-12-29 | 40 |  | Red - information uncertain
4721 | Building and installation, Järfälla tunnel and stations | Including framework completion Installations (building incl. telecom) | Building and installation works | Barkarby | Precualification in TransQ is required | Yes 9.4.1 – 9.4.9 or 9.4.99 | Build only contract | ongoing | Ongoing procurement | 2021-02-01 | 2021-03-01 | 500-1,000 |  | Green - information certain (within 3 months) | Red - information uncertain
4743 | Track, Electricity 400 volt, 3:rd rail, ducting | Järfällatunneln, BEST Track (Track-, Electrical-, Signal- and Telecommunication works) | BEST (Track-, Electrical-, Signal- and Telecommunication works) | Barkarby | Precualification in TransQ is required | Yes 9.1.1 | Build only contract | Qualification of suppliers will be conducted in connection with evaluation of tenders | 2021-01-04 | 2021-06-30 | 2021-10-01 | 250-300 |  | Green - information certain (within 3 months) | Red - information uncertain | No separat qualification in october. Former procurement ID nr 4742 is included in 4743
4744 | Signal | BEST Signal (Track-, Electrical-, Signal- and Telecommunication works) | BEST (Track-, Electrical-, Signal- and Telecommunication works) | Barkarby | Precualification in TransQ is required | Yes 9.1.1 | Build only contract | 2021-01-04 | 2021-04-01 | 2021-09-30 | 2022-01-01 | 25 |  | Yellow- relativly certain information | Red - information uncertain
5711 | Kvicksundsvägen, Concrete tunnel | Construction of a concrete tunnel, including preparatory works, sheeting, earth and rock excavation, grouting and reinforcement works. Pipe rerouting. | Rock excavation and civil works | Depot | Precualification in TransQ is required | Yes 9.4.1 – 9.4.9 or 9.4.99 | Build only contract | Completed | Ongoing procurement | 2021-01-25 | 2021 Q1 | 300-500 |  | Green - information certain (within 3 months) | Red - information uncertain | Railway plan, and Environmental ruling - estimated 2020- Q4
5712 | Access tunnel (excl. concrete tunnel) Örbyleden | Mainly including preparatory works, sheeting, earth and rock excavation, including injection and reinforcement works. | Rock excavation and civil works | Depot | Precualification in TransQ is required | Yes 9.4.3 | Build only contract | Completed | Ongoing procurement | 2021-01-13 | 2021-Q1 | 50-100 |  | Green - information certain (within 3 months) |  | Railway plan, and Environmental ruling - estimated 2020- Q4
5713 | Main tunnel, connecting tracks and sidings hall. Interior fittings and installations in underground tunnel and cavern. | Excavation of main cavern and connecting tunnels. Installations in access- and service tunnel, connecting track and storage hall below ground. (Sprinklers, lighting, etc.) | Rock excavation and civil works | Depot | Precualification in TransQ is required | Yes 9.4.1 – 9.4.9 or 9.4.99 | Build only contract | Qualification of suppliers will be conducted in connection with evaluation of tenders | 2021-04-15 | 2021 Q4 | 2022 Q1 | 600-700 |  | Yellow- relativly certain information | Red - information uncertain | Railway plan, and Environmental ruling - estimated 2020- Q4 Also including former procurement 5726
5721 | Expanded sidings shed Extension of existing building Workshop area New cleaning and siding shed | Existing buildning above ground to be expanded with a garaging point for 4 trains. Extension of existing cleaning shed A new workshop (C30), approximately 80x10 metres shall be built. Construction of a new building with a garaging point for 8 trains. | Building and installation works | Depot | Precualification in TransQ is required | Yes 9.4.1 – 9.4.9 or 9.4.99 | Design & Build Contract | ongoing | Ongoing procurement | Ongoing evaluation | 2020-Q3 | 800-1000 |  | Green - information certain (within 3 months) | Red - information uncertain | The procurment is including former ID 5722, 5723 and 5724
5740 | BEST (Track, Electric power, Signal- and Telecommunication) | BEST Includes all new Track-, Electrical power, Signal , Telecommunication installations and channeling within exiting depot in Högdalen and new tunnel between existing depot and greenline ( Farstabanan) | BEST (Track-, Electrical-, Signal- and Telecommunication works) | Depot | Precualification in TransQ is required | Yes 9.1.1 | Build only contract | 2021-11-30 | 2021-05-31 | 2021-11-01 | 2022-01-31 | 100-300 |  | Green - information certain (within 3 months) | Red - information uncertain | Railway plan, and Environmental ruling - estimated 2020- Q4
7711 | Rail and service tunnel Kungsträdgården (Ktg) | The contract comprises rock shafts for rail tunnels and service on Blasieholmen. Concreting works and connecting earth works for ways up and entrances are also included. | Rock excavation and civil works | Södermalm | Precualification in TransQ is required | Yes | Build only contract | Ongoing procurement | Ongoing procurement | 2021-01-04 | 2020-02-15 | 300-500 |  | Green - information certain (within 3 months) | Red - information uncertain | the previous procurement has been canceled and will now be redone.
7715 | Civil works Sofia | The contract comprises a rock shaft for rail tunnel and station areas. Concreting works and connecting earth works for ways up and entrances are also included. The greatest depth of the facility is at the passage under Saltsjön. The new facility connects to the existing station Kungsträdgården. | Rock excavation and civil works | Södermalm | Precualification in TransQ is required | Yes 9.4.1 – 9.4.9 or 9.4.99 | Build only contract | ongoing | Ongoing procurement | Ongoing evaluation | 2020-10-30 | 500-1000 |  | Green - information certain (within 3 months)
7716 | Civil works Hammarby kanal | The contract comprises a rock shaft for rail tunnel and station areas at Sofia and Hammarby kanal. Concreting works and connecting earth works for ways up and entrances are also included. | Rock excavation and civil works | Södermalm | Precualification in TransQ is required | Yes 9.4.1 – 9.4.9 or 9.4.99 | Build only contract | Qualification of suppliers will be conducted in connection with evaluation of tenders | 2021-03-01 | 2021-10-01 | 2022-Q1 | 500-1000 |  | Green - information certain (within 3 months) | Red - information uncertain
8714 | Civil works Sickla | Rock shaft for rail tunnel, holding tracks and station spaces and concreting works as well as connecting earth works. | Rock excavation and civil works | Nacka | Qualification in TransQ is required | Yes 9.4.1 – 9.4.9 or 9.4.99 | Build only contract | Qualification of suppliers will be conducted in connection with evaluation of tenders | 2020-11-15 | 2021-05-31 | 2021-12-01 | 500-1000 |  | Green - information certain (within 3 months)
8715 | Civil works Järla | Rock shaft for rail tunnel, holding tracks and station spaces and concreting works as well as connecting earth works. | Rock excavation and civil works | Nacka | Qualification in TransQ is required | Yes 9.4.1 – 9.4.9 or 9.4.99 | Build only contract | Qualification of suppliers will be conducted in connection with evaluation of tenders | 2021-06-15 | 2022-01-15 | 2022 Q2 | 500-1000 |  | Red - information uncertain
8716 | Civil worksNacka | Rock shaft for rail tunnel, holding tracks and station spaces and concreting works as well as connecting earth works. | Rock excavation and civil works | Nacka | Precualification in TransQ is required | Yes 9.4.1 – 9.4.9 or 9.4.99 | Build only contract | Completed | Ongoing procurement | 2020-11-16 | 2021 Q3 | 500-1000 |  | Green - information certain (within 3 months) | Red - information uncertain
9712 | Civil works Sockenplan , stage 2 / Slakthusområdet | Rock shafts for rail tunnel and station spaces and concreting works and connecting earth works. | Rock excavation and civil works | Söderort | Precualification in TransQ is required | Yes 9.4.1 – 9.4.9 or 9.4.99 | Build only contract | Qualification of suppliers will be conducted in connection with evaluation of tenders | 2021-09-27 | 2022 Q2 | 2022 Q2/Q4 | 500-1000 |  | Red - information uncertain
9713 | Civil works Sockenplan stage 3 | Rock shafts for rail tunnel and station spaces and concreting works and connecting earth works. | Rock excavation and civil works | Söderort | Precualification in TransQ is required | Yes 9.4.1 – 9.4.9 or 9.4.99 | Build only contract | 2028 Q3 | 2028 Q3 | 2029 Q1 | 2029 Q2 | 50-100 |  | Red - information uncertain
9715 | Civil works Gullmarsplan | Rock shafts for rail tunnel and station spaces and concreting works and connecting earth works. | Rock excavation and civil works | Söderort | Precualification in TransQ is required | Yes 9.4.1 – 9.4.9 or 9.4.99 | Build only contract | ongoing | Ongoing procurement | 2021-03-14 | 2021-05-31 | > 1 000 |  | Green - information certain (within 3 months) | Red - information uncertain
15015 | Framework contract for removing graffiti | Framework contract for removing graffiti on plank | Other | All projects | No registration or prequalification is required | No | Service | n/a | 2020-11-01 | data will be completed | data will be completed | Unavailable |  | Green - information certain (within 3 months)
15022 | Design of Metro to Älvsjö | Design of Metro to Älvsjö | Other | Älvsjö | Registration with consultant broker i required | No | Service | not applicable | 2021-Q3 | 2021-Q4 | 2022-Q1 | 250-300 |  | Red - information uncertain
15023 | Framwork contract- hotels | Temporary stay | Other | All projects | No registration or prequalification is required | No | Service | n/a | 2020-10-30 | data will be completed | data will be completed | Unavailable |  | Green - information certain (within 3 months)
15024 | Framework contract - apartment hotels | Temporary stay | Other | All projects | No registration or prequalification is required | No | Service | n/a | 2020-11-01 | data will be completed | data will be completed | Unavailable |  | Green - information certain (within 3 months)
15025 | Framework contract- office hotels | Temporary stay | Other | All projects | No registration or prequalification is required | No | Service | n/a | 2020-11-15 | data will be completed | data will be completed | Unavailable |  | Green - information certain (within 3 months)
26721 | Lifts | Vertical elevators for 7 stations for Kungsträdgården - Nacka and Sofia - Sockenplan | Installations works | Nacka-southern suburbs | Precualification in TransQ is required | Yes 4.2.7 | Design & Build Contract | 2022-07-01 | 2022-08-01 | 2022-12-01 | 2023-02-01 | 50-75 |  | Red - information uncertain
26722 | Inclined lifts | Inclined elevatorsfor 7 stations for Kungsträdgården - Nacka and Sofia - Sockenplan | Installations works | Nacka-southern suburbs | Precualification in TransQ is required | Yes 4.2.7 | Design & Build Contract | 2022-07-01 | 2022-08-01 | 2022-12-01 | 2023-02-01 | 50-75 |  | Red - information uncertain
26723 | Escalators < 30 m | Escalators < 30 meter for 7 stations for Kungsträdgården - Nacka and Sofia - Sockenplan | Installations works | Nacka-southern suburbs | Precualification in TransQ is required | Yes 4.2.6 | Design & Build Contract | 2021-07-31 | 2021-08-31 | 2021-12-31 | 2022-04-01 | 550-700 |  | Red - information uncertain
26724 | Escalators > 30 m | Escalators > 30 meter for 7 stations for Kungsträdgården - Nacka and Sofia - Sockenplan | Installations works | Nacka-southern suburbs | Precualification in TransQ is required | Yes 4.2.6 | Design & Build Contract | 2021-07-31 | 2021-08-31 | 2021-12-31 | 2022-04-01 | 250-350 |  | Red - information uncertain
26725 | Fire- and tunnelventilation | Plumbing, pumping stations and ventilation for 7 stations for Kungsträdgården - Nacka and Sofia - Sockenplan | Installations works | Nacka-southern suburbs | Precualification in TransQ is required | Yes 4.3.0 4.3.1 – 4.3.4 or 4.3.99 | Design & Build Contract | 2021-03-01 | 2021-04-01 | 2021-12-31 | 2022-04-01 | 200-400 |  | Red - information uncertain
26726 | Installationwork 7 stations | Electricity 400V, Telecom, and BMS for 7 stations for Kungsträdgården - Nacka and Sofia - Sockenplan | Installations works | Nacka-southern suburbs | Precualification in TransQ is required | Yes 9.4.1 – 9.4.9 or 9.4.99 | Design & Build Contract | 2021-03-01 | 2021-04-01 | 2021-12-31 | 2022-04-01 | 700-800 |  | Red - information uncertain
26727 | Plumbing, pumping stations and ventilation | Plumbing, pumping stations and ventilation for 7 stations for Kungsträdgården - Nacka and Sofia - Sockenplan | Installations works | Nacka-southern suburbs | Precualification in TransQ is required | Yes 9.4.9 | Design & Build Contract | 2021-03-01 | 2021-04-01 | 2021-12-31 | 2022-04-01 | 200-300 |  | Red - information uncertain
26741 | Stadshagen - Civil and building works | Civil and building works for new rectifire substation above ground in Stadshagen | Civil and building works | Nacka-southern suburbs | Precualification in TransQ is required | Yes | Build only contract | 2022-Q1 | 2022-Q2 | 2022-Q3 | 2022- Q4 | 5-10 |  | Red - information uncertain
26743 | Electricity 400V, Telecom | Electricity 400V, Telecom. For Kungsträdgården - Nacka and Sofia - Sockenplan | BEST (Track-, Electrical-, Signal- and Telecommunication works) | Nacka-southern suburbs | Precualification in TransQ is required | Yes 9.1.1 | Build only contract | 2022 Q3 | 2022 Q4 | 2023 Q2 | 2023 Q3 | 50-100 |  | Red - information uncertain | Red - information uncertain
26745 | Mouting ducting and cabling | Mouting ducting och cabling. For Kungsträdgården - Nacka and Sofia- Sockenplan | BEST (Track-, Electrical-, Signal- and Telecommunication works) | Nacka-southern suburbs | Precualification in TransQ is required | Yes 9.1.1 | Build only contract | 2022 Q4 | 2023 Q1 | 2023 Q3 | 2023 Q4 | 50-100 |  | Red - information uncertain | Red - information uncertain
267421 | Track, walking path, Third rail 750V. | Track work, troughs, Thrid rail 750 V . For Kungsträdgården - Hammarby Kanal and Sofia- Sockenplan | BEST (Track-, Electrical-, Signal- and Telecommunication works) | Nacka-southern suburbs | Precualification in TransQ is required | Yes 9.1.1 | Build only contract | 2022 Q1 | 2022 Q1 | 2022 Q3 | 2022 Q4 | 300-500 |  | Red - information uncertain | Red - information uncertain
267422 | Track, walking path, Third rail 750V. | Track work, troughs, Thrid rail 750 V . For Hammarby Kanal - Nacka | BEST (Track-, Electrical-, Signal- and Telecommunication works) | Nacka-southern suburbs | Precualification in TransQ is required | Yes 9.1.1 | Build only contract | 2022 Q1 | 2022 Q1 | 2022 Q3 | 2022 Q4 | 300-500 |  | Red - information uncertain
267441 | Signal | Signalinstallation for Kungsträdgården - Nacka and Sofia - Sockenplan | BEST (Track-, Electrical-, Signal- and Telecommunication works) | Nacka-southern suburbs | Precualification in TransQ is required | Yes 9.1.1 | Build only contract | 2023 Q1 | 2023 Q2 | 2023 Q4 | 2024 Q1 | 100-300 |  | Red - information uncertain | Red - information uncertain
26611 | Vertical transport- high velocoty elevators | 19 High velocity elevators for the stations Sofia, Nacka C and Gullmarsplan | Installations works | Nacka-southern suburbs | Precualification in TransQ is required | Yes 4.2.7 | Design & Build Contract | 2022-07-01 | 2022-08-01 | 2022-12-01 | 2023-02-01 | 100-200 |  | Yellow- relativly certain information

## template
Uppdrag | Projekt | Registrering hos konsultmäkl | Transq | Entreprenadform | Kostnad | Upphandlare | Sannolikhet
Framework agreement | Barkarby | Precualification in TransQ is required | Yes 9.1.0 | Build only contract | 0-5 | Anders Karnestrand | Green - information certain (within 3 months)
Preparatory work | Arenastaden | Registration with consultant broker i required | Yes 9.4.1 – 9.4.9 or 9.4.99 | Design & Build Contract | 5-20 | Cecilia Tennfors | Red - information uncertain
| All projects | No registration or prequalification is required | Yes 9.1.1 |  |  |  | Yellow- relativly certain information
Access tunnel works | Depå |  | Yes 9.4.6 | Combo | 20-50 | Pia Lindberg-Nedby | Data not available
Rock excavation and civil works | Nacka |  | Yes 9.4.7 | Service | 50-100 | Peter Malmsten
Building and installation works | Söder |  | Yes 9.4.3 |  | 100-300
Installation | Söderort |  | No |  | 300-500
BEST (Track-, Electrical-, Signal- and Telecommunication works) | Södermalm |  |  |  | 500-1 000
Other | Älvsjö |  |  |  | > 1 000
Combination | All projects |  |  |  | Data missing